## Sheet1
Month | Task | Progress Status | Draft Submission Required
January | Initial Preparation, Latex Installation, Thesis layout setup | In Progress | No
February | Literature Review, Research Aim, Research Question, Theoritical Background | In Progress | Yes
March | Current State of Art, Research Methodology, Learning Spark , Envisaging what to do in Application | Not Started | Yes
April | Start working on Application and Result Part, Data Collection | Not Started | No
May | Keep working on Result, Data Collection and Analysis (Get to know about the Qlik Application Systems) | Not Started | No
June | Keep working on Result | Not Started | Yes
July | Complete Result and Discussion part of the thesis writing | Not Started | No (Summer)
August | Complete the thesis with Conclusion and Abstract | Not Started | Yes
September | Wrapping Up University Presentation and Two Opposition | Not Started | Yes